## Customization List
Sl. No | Customization List | Type of Cust | Developers | Start Date | End Date | Phase | Status | Priority | Remarks | Intitate | Online Page[F] | Critical | Phase I
1 | Campus ID Generation | Online Page[F] | Yadvendra |  |  | Phase I | Production | Critical |  | In Progress | Appl Eng[C] | Easy | Phase II
2 | Campus ID Generation | Reports[R] | Yadvendra |  |  | Phase I | Production | Critical |  | Unit Testing | Reports[R] | Medium
3 | Campus ID Update | Appl Eng[C] | Mahesh |  |  | Phase I | Production | Critical |  | UAT | IB[C]
4 | Student Fee Receipt | Reports[R] | Yadvendra |  |  | Phase I | Production | Critical |  | Complete | Security[W]
5 | Statement of Grade(Yearly) | Reports[R] | Yadvendra |  |  | Phase I | UAT | Critical | Facing some Technical problems | Production | Scratch Customization
6 | Statement of Grade(Semester Wise) | Online Page[F] | Yadvendra |  |  | Phase I | UAT | Critical | Completed but not migrated to PROD since UAT is refreshed |  | Dashboard
7 | Statement of Grade(Semester Wise) | Online Page[F] | Yadvendra |  |  | Phase I | UAT | Critical | Completed but not migrated to PROD since UAT is refreshed
8 | Cash Book - Per Day Report | Reports[R] | Yadvendra |  |  | Phase I | Production | Medium
9 | Cash Book - Summary Report | Reports[R] | Yadvendra |  |  | Phase I | Production | Medium | Late due to some Date related transaction
10 | Open Purchase Order Report | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (Removing of Alt Acct, Oper Unit, Fund, Department, Program, Class, Bud Ref, Product, Project columns from the SQR Report) - OPEN PO LOOKUP
11 | PO Detail Listing by PO Date | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (Inserting Extra Column and Modifying query for Supplier name)
12 | Requisition | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (mfg ID and price are not required)
13 | Request for Quotation | Online Page[F] | Yadvendra |  |  | Phase I | Complete | Easy | (No need of mfg ID, mfg item ID, and freight terms on quotation page)
14 | Student Balance Record | Reports[R] | Tushar | 2013-10-17 | 2013-10-19 | Phase II | Production | Medium
15 | Detailed Student Balance | Reports[R] | Tushar | 2013-10-21 |  | Phase II | In Progress | Medium | Concession,And Immediate payment issue need to be discussed with client
16 | Student Id card | Reports[R] | Tushar | 2013-10-22 |  | Phase II | In Progress | Medium | Photo Card Issue,bar code font to be embedded in pdf reader
14 | Student Assignment Marks | Reports[R] | Krishnarajs |  |  | Phase I | Unit Testing | Medium | Needs to be verified and improved.
18 | Student Elective |  |  |  |  | Phase II | Intitate | Critical | Documentation initiated by yadvendra.
19 | Faculty Lecture Elective |  |  |  |  | Phase II | Intitate | Critical
20 | Student Feedback | Scratch Customization | Ankita |  |  | Phase II | Intitate | Critical
21 | Lecture Plan of Instructor |  |  |  |  | Phase II | Intitate | Critical
22 | Quality Check |  |  |  |  | Phase II | Intitate | Critical
23 | ID Card Photo |  | Ankita |  |  | Phase II | In Progress | Critical
24 | Recurrence IB |  | Krishnarajs,Ankita |  |  | Phase II | Intitate | Critical
25 | Student Attendance subject wise | Reports[R] | Ankita |  |  | Phase I | Complete | Medium
26 | Student Attendance overall | Reports[R] | Ankita |  |  | Phase I | Complete | Medium
27 | Faculty Attendance Marking for 3 days | Security[W] | Ankita |  |  | Phase II | Complete | Medium | removed the some code default = N
28 | Student Assignment Marks | Reports[R] | Krishnarajs |  |  | Phase I | Unit Testing | Medium | Needs to be verified and improved.
29 | Term Activation production issue | Online Page[F] | Krishnarajs,Ankita | 2013-11-07 | 2013-11-08 | Phase II | Complete | Medium | Fixed in production
30 | Faculty Attendance Marking for 3 days |  | Ankita |  |  | Phase II | Complete | Critical | removed the some code default = N
31 | Gradebook marks feed disable |  | Ankita |  |  | Phase II | Complete | Critical
32 | Plan change once |  | Ankita |  |  | Phase II | Complete | Critical
33 | Student Elective |  |  |  |  | Phase II | Intitate | Critical | Documentation initiated by yadvendra.
34 | Faculty Lecture Elective |  |  |  |  | Phase II | Intitate | Critical
35 | Student Feedback |  |  |  |  | Phase II | Intitate | Critical
36 | Lecture Plan of Instructor |  |  |  |  | Phase II | Intitate | Critical
37 | Quality Check |  |  |  |  | Phase II | Intitate | Critical
38 | ID Card & Barcode |  | Ankita |  |  | Phase II | Complete | Critical
39 | Facility Table |  | Ankita |  |  | Phase II | Complete | Critical
40 | Student Report debit & credit |  | Ankita |  |  | Phase II | Complete | Critical
41 | Faculty/Staff User profile Creation | Online Page[F] | Ankita |  |  | Phase I | Complete | Medium
42 | Registration Form | Security[W] | Roli Nigam | 2013-09-17 | 2013-09-30 | Phase I | In Progress | Easy | Student Category, Hostel Info, Privious Academic info
43 | Campus & Finance IB |  | Ankita |  |  | Phase II | Complete | Critical
44 | Recurrence IB |  | Krishnarajs,Ankita |  |  | Phase II | Intitate | Critical
45 | Batch IB Setup In Production | IB[C] | Ankita | 2013-11-01 | 2013-11-01 | Phase I | Complete | Critical
46 | Faculty Timetable | Reports[R] | Roli Nigam | 2013-01-10 | 2013-05-10 | Phase I | Cancelled | Medium
47 | Monthly Attendance | Reports[R] | Roli Nigam | 2013-07-10 | 19/10/2013 | Phase II | In Progress | Critical | Differed to Sachin
48 | Tabular Report of Each Semester | Reports[R] | Roli Nigam | 2013-10-21 |  | Phase II | In Progress | Critical
49 | One Letter for Communication | Reports[R] | Ankita | 2013-10-31 | 2013-11-01 | Phase II | Complete | Medium | Not in Production
50 | Data Deletion from Database for Voucher, Supplier,and journals |  | Roli Nigam |  |  | Phase II | Completed | Critical
51 | Weekly Attendance | Reports[R] | Sachin | 2013-10-22 | 30/10/2013 | Phase II | In Progress | Critical | On Hold
52 | Monthly Attendance | Reports[R] | Sachin | 2013-10-22 | 30/10/2013 | Phase II | Complete | Critical
53 | Gradebook Customization | Online Page[F] | Ankita | 2013-10-28 | 2013-11-01 | Phase II | Complete | Critical | Not in Production
54 | ID Card Barcode | Reports[R] | Ankita | 2013-11-01 | 2013-11-01 | Phase II | Complete | Critical | Not in Production
55 | E-mail Notification Security | Online Page[F] | Ankita |  |  | Phase II | Intitate | Medium
56 | Photo in Prod upload | Online Page[F] | Krishnarajs,Ankita | 2013-11-05 |  |  | In Progress
57 | Account data Push in prod | IB[C] | Ankita | 2013-11-05 | 2013-11-05 | Phase II | In Progress | Medium
58 | Gradebook New requirement modifications | Online Page[F] | Ankita | 2013-11-07 | 2013-11-07 | Phase II | Complete | Critical | Testing Required by SRMU members
59
60 | Permission given to migrated projects | Security[W] | Ankita | 2013-11-07 | 2013-11-07 | Phase II | Complete | Medium | In production
61 | Communication Reports +4 | Reports[R] | Tushar | 2013-11-06 |  | Phase II | In Progress | Medium
62 | Cash Book Summary | Reports[R] | Tushar | 2013-10-28 | 2013-10-30 | Phase II | Production | Medium
63 | Lecture Plan/Activity | Reports[R] | Tushar |  |  | Phase II | Intitate
64 | Attendance Customization |  | Yadvendra | 28/10/13 | 30/10/13 | Phase II | Open | Critical
65 | Student Elective | Online Page[F] | Yadvendra |  |  | Phase II | Intitate | Medium | Documentation initiated by yadvendra.
66 | PO requisition | Online Page [F] | Yadvendra | 41586 |  | Phase II | In Progress | Medium
67 | Dashboard(RND) | Dashboard | Sachin | 41585 |  | Phase II | Initiate | Medium | RND

## 04-Nov-2013to09-Nov-13
S.No. | Customization List | Type Of Customization | Developer | Start Date | End Date | Phase II | Status | Priority | Remarks
1 | Gradebook New requirement modifications | Online Page[F] | Ankita | 2013-11-07 | 2013-11-07 | Phase II | Complete | Critical | Testing Required by SRMU members
2 | Term Activation production issue | Online Page[F] | Krishnarajs,Ankita | 2013-11-07 | 2013-11-08 | Phase II | Production | Medium | Fixed in production
3 | Permission given to migrated projects | Security[W] | Ankita | 2013-11-07 | 2013-11-07 | Phase II | Production | Medium | In production
4 | Student Feedback | Scratch Customization | Ankita | 2013-11-09 |  | Phase II | Intitate | Critical
5 | Communication Reports + 4 | Reports[R] | Tushar | 2013-11-06 |  | Phase II | In Progress | Medium | 1 completed,2(almost same issue i.e year)
6 | Transcript | Reports[R] | Yadvendra | 2013-11-08 |  | Phase II | In Progress | Medium
7 | Field Customization(PO) | Online Page[F] | Yadvendra | 2013-11-08 |  | Phase II | In Progress | Medium
8 | Student Elective(Process) |  | Yadvendra | 2013-11-09 |  | Phase II | Initiate | Medium
9 | Templates(HRMS);job_data,personal_data,accumalator,absence | Data Migration | Roli | 2013-11-06 |  | Phase II | In Progress | Critical
10 | Dashboard | Dashboard | Sachin | 2013-11-07 |  | Phase II | Initiate | Medium | Seeking Attendance templates,licence for dashboard tools