## Customization List
Sl. No | Customization List | Type of Cust | Developers | Start Date | End Date | Phase | Status | Priority | Remarks | Intitate | Online Page[F] | Critical | Phase I
1 | Campus ID Generation | Online Page[F] | Yadvendra |  |  | Phase I | Production | Critical |  | In Progress | Appl Eng[C] | Easy | Phase II
2 | Campus ID Generation | Reports[R] | Yadvendra |  |  | Phase I | Production | Critical |  | Unit Testing | Reports[R] | Medium
3 | Campus ID Update | Appl Eng[C] | Mahesh |  |  | Phase I | Production | Critical |  | UAT | IB[C]
4 | Student Fee Receipt | Reports[R] | Yadvendra |  |  | Phase I | Production | Critical |  | Complete | Security[W]
5 | Statement of Grade(Yearly) | Reports[R] | Yadvendra |  |  | Phase I | UAT | Critical | Facing some Technical problems | Production
6 | Statement of Grade(Semester Wise) | Online Page[F] | Yadvendra |  |  | Phase I | UAT | Critical | Completed but not migrated to PROD since UAT is refreshed
7 | Statement of Grade(Semester Wise) | Online Page[F] | Yadvendra |  |  | Phase I | UAT | Critical | Completed but not migrated to PROD since UAT is refreshed
8 | Cash Book - Per Day Report | Reports[R] | Yadvendra |  |  | Phase I | Production | Medium
9 | Cash Book - Summary Report | Reports[R] | Yadvendra |  |  | Phase I | Production | Medium | Late due to some Date related transaction
10 | Open Purchase Order Report | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (Removing of Alt Acct, Oper Unit, Fund, Department, Program, Class, Bud Ref, Product, Project columns from the SQR Report) - OPEN PO LOOKUP
11 | PO Detail Listing by PO Date | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (Inserting Extra Column and Modifying query for Supplier name)
12 | Requisition | Reports[R] | Yadvendra |  |  | Phase I | Complete | Easy | (mfg ID and price are not required)
13 | Request for Quotation | Online Page[F] | Yadvendra |  |  | Phase I | Complete | Easy | (No need of mfg ID, mfg item ID, and freight terms on quotation page)
14 | Student Balance Record |  | Tushar | 2013-10-17 | 2013-10-19 | Phase II | Complete | Critical | In production
15 | Detailed Student Balance |  | Tushar | 21/10/2013 |  | Phase II | WIP | Critical
16 | Student Id card |  | Tushar | 22/10/2013 |  | Phase II | WIP | Critical
14 | Student Assignment Marks | Reports[R] | Krishnarajs |  |  | Phase I | Unit Testing | Medium | Needs to be verified and improved.
18 | Student Elective |  |  |  |  | Phase II | Intitate | Critical | Documentation initiated by yadvendra.
19 | Faculty Lecture Elective |  |  |  |  | Phase II | Intitate | Critical
20 | Student Feedback |  |  |  |  | Phase II | Intitate | Critical
21 | Lecture Plan of Instructor |  |  |  |  | Phase II | Intitate | Critical
22 | Quality Check |  |  |  |  | Phase II | Intitate | Critical
23 | ID Card |  | Ankita |  |  | Phase II | WIP | Critical
24 | Recurrence IB |  | Krishnarajs,Ankita |  |  | Phase II | Intitate | Critical
15 | Student Attendance subject wise | Reports[R] | Ankita |  |  | Phase I | Complete | Medium
16 | Student Attendance overall | Reports[R] | Ankita |  |  | Phase I | Complete | Medium
17 | Faculty Attendance Marking for 3 days | Security[W] | Ankita |  |  | Phase II | Complete | Medium | removed the some code default = N
18 | Student Assignment Marks | Reports[R] | Krishnarajs |  |  | Phase I | Unit Testing | Medium | Needs to be verified and improved.
30 | Faculty Attendance Marking for 3 days |  | Ankita |  |  | Phase II | Complete | Critical | removed the some code default = N
31 | Gradebook marks feed disable |  | Ankita |  |  | Phase II | Complete | Critical
32 | Plan change once |  | Ankita |  |  | Phase II | Complete | Critical
33 | Student Elective |  |  |  |  | Phase II | Intitate | Critical | Documentation initiated by yadvendra.
34 | Faculty Lecture Elective |  |  |  |  | Phase II | Intitate | Critical
35 | Student Feedback |  |  |  |  | Phase II | Intitate | Critical
36 | Lecture Plan of Instructor |  |  |  |  | Phase II | Intitate | Critical
37 | Quality Check |  |  |  |  | Phase II | Intitate | Critical
38 | ID Card & Barcode |  | Ankita |  |  | Phase II | WIP | Critical
39 | Facility Table |  | Ankita |  |  | Phase II | Complete | Critical
40 | Student Report debit & credit |  | Ankita |  |  | Phase II | Complete | Critical
19 | Faculty/Staff User profile Creation | Online Page[F] | Ankita |  |  | Phase I | Complete | Medium
43 | Campus & Finance IB |  | Ankita |  |  | Phase II | Complete | Critical
44 | Recurrence IB |  | Krishnarajs,Ankita |  |  | Phase II | Intitate | Critical
20 | Registration Form | Security[W] | Roli Nigam | 2013-09-17 | 2013-09-30 | Phase I | In Progress | Easy | Student Category, Hostel Info, Privious Academic info
21 | Faculty Timetable | Reports[R] | Roli Nigam | 2013-01-10 | 2013-05-10 | Phase I | Cancelled | Medium
47 | Monthly Attendance |  | Roli Nigam | 2013-07-10 | 19/10/2013 | Phase II | In Progress | Critical | Differed to Sachin
48 | Tabular Report of Each Semester |  | Roli Nigam | 2013-10-21 |  | Phase II | In Progress | Critical
50 | Data Deletion from Database for Voucher, Supplier,and journals |  | Roli Nigam |  |  | Phase II | Completed | Critical
51 | Weekly Attendance |  | Sachin | 2013-10-22 | 30/10/2013 | Phase II | WIP | Critical | Query part done,page creation and report designing left
52 | Monthly Attendance |  | Sachin | 2013-10-22 | 30/10/2013 | Phase II | WIP | Critical
53
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
| Attendance Customization |  | Yadvendra | 28/10/13 | 30/10/13 | Phase II | Open | Critical
| Student Electives | [5 empty] | Open | Medium
| Course Plan | [6 empty] | Medium
22 | ID Card | Reports[R] | Ankita |  |  | Phase II | WIP | Easy
23 | Campus & Finance IB with Recurrence | Appl Eng[C] | Krishnarajs,Ankita |  |  | Phase II | Intitate | Medium
24 | Monthly Attendance | Reports[R] | Roli |  |  | Phase I | WIP | Medium | Difficulty of dynamic columns in subjects.
25 | Date wise student attendance | Reports[R] | Sachin |  |  | Phase II | WIP | Medium
26 | TR report | Reports[R] | Roli |  |  | Phase II | WIP | Critical
27 | Gradebook marks feed disable | Security[W] | Ankita |  |  | Phase II | Complete | Medium
28 | Plan change once | Security[W] | Ankita |  |  | Phase II | Complete | Medium
29 | Student Elective | Online Page[F] |  |  |  | Phase II | Intitate | Medium | Documentation initiated by yadvendra.
30 | Faculty Teaching Choice | Online Page[F] |  |  |  | Phase II | Intitate | Medium
31 | Student Feedback | Online Page[F] |  |  |  | Phase II | Intitate | Easy
32 | Lecture Plan of Instructor | Online Page[F] |  |  |  | Phase II | Intitate | Medium
33 | Student Report debit & credit | Reports[R] | Ankita |  |  | Phase II | Complete | Medium
34 | Student Balance Record | Reports[R] | Tushar