## Sheet1
Ricefw ID | Type | area | module | report | PS delivered | Srmu required | Fit/gap | Name/sample report | DESCRIPTION | REQUIRMENT ID | Priority | STATUS | OWNER | PRODUCTION
| Reports | campus | Student financials | list of all students who has balance till date | N | Y | GAP | Student balance record | Based on filter(i.e. academic program,term)eg-MBA01,1201 |  | post GoLive | Completed | Tushar | Moved
| Reports | campus | Student financials |  | N | Y | GAP | Detailed Student balance record | Detailed record according to academic program,term eg-bus,hostel,course fees |  | post GoLive | WIP | Tushar | NO
| REports | campus | Student financials |  | N | Y | GAP | ID Card | SRMU student id card |  | psotGoLive | WIP | Tushar | NO
| Reports | campus | Student financials |  | N | Y | GAP | Cash Book Summary | To print cash book between 2 particular dates (i.e. from date and to date) |  | post GoLive | Completed | Tushar | NO